## Summary
Module | Total | Open | In Progress | Ready for Retest | Reopened | Closed | Won't Fix | Needs Decision | Critical | High | Medium | Low
Login (mobile sign-in) | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 3
Campaigns (WhatsApp) | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3
Broadcasts (WhatsApp) | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
Total | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 2 | 7
Failures to triage (no linked defect): 9. Status and columns O-U are kept between updates; a defect with a guard test moves to "Ready for Retest" or "Reopened" automatically (see tools\excel\update-workbooks.js).

## Login
No# | Module/Screen / Extension | Section / Category | Task / Bugs / Enhacement | Steps to Reproduce (If required) | Expected Result | Actual Result | Date | Issue Type | Severity | Priority | Status | Test Environment | Screenshot/Video | Reopen SS/Video & Description | Assigned To | Closed / Resolved by | Requested by | QA Comment | Developer / Designer Comment | Closed Date
1 | Login (mobile sign-in) | Validation | MLGN-D01 - Sign-in request is sent even though the email failed the app's own format check | 1. Launch the app (signed out). 2. Email: not-an-email 3. Password: Secret123 4. Tap "Sign in". | Only the inline error "Enter a full email, like you@company.com." is shown and no request is made, the same way empty fields are blocked (MLGN-008). | The inline error is shown, but the form is submitted anyway: the button changes to "Signing in..." and the server then answers with a second banner, "Invalid email". The user sees two messages for one problem, and the backend receives a request the client already knew was invalid. Also seen with the SQL-injection input (MLGN-013). | 2026-10-29 12:34 | Bug | Low | P4 - Low | Open | Beta backend: accountsbeta.saleshiker.com; see QA comment | [5 empty] | Automated test: MLGN-012 (test/specs/regression/login-validation.spec.ts). Reproduced on Android 15 (API 35) and Android 17 (API 37) emulators. The test is left failing on purpose until this is fixed.
2 | Login (mobile sign-in) | Validation | MLGN-D02 - No client-side length check on the email field | 1. Launch the app (signed out). 2. Email: 250 x "a" + "@example.com" 3. Password: Secret123 4. Tap "Sign in". | The app rejects an address whose part before "@" exceeds 64 characters (RFC 5321) before sending it, or caps the field length. | The full value is accepted and sent; the server replies "Email or password is wrong.". No crash, and the generic message is acceptable, but invalid input still reaches the backend. | 2026-10-29 12:34 | Observation | Low | P4 - Low | Needs Decision | Beta backend: accountsbeta.saleshiker.com; see QA comment | [5 empty] | Automated test: MLGN-015 passes (it checks that the app copes safely). Product to decide whether a client-side limit is wanted.
3 | Login (mobile sign-in) | Testability | MLGN-D03 - Sign-in controls have no testID / resource-id | 1. Open the sign-in screen. 2. Inspect the view hierarchy (Appium page source, or adb shell uiautomator dump). | Inputs, buttons and links expose stable ids (React Native testID), e.g. login-email, login-password, login-submit. | No app resource-ids exist. Automation has to use accessibility labels, which change with copy or localisation. | 2026-10-29 12:34 | Enhancement | Low | P4 - Low | Open | Beta backend: accountsbeta.saleshiker.com; see QA comment | Hierarchy dump: reports/*-evidence-*/hierarchy.csv (no com.saleshiker.app:id/* except action_bar_root) |  |  |  |  | Not a functional defect. Once ids are added, only the selectors in src/pages/*.ts need updating.
4 | Login (mobile sign-in) | Stability | MLGN-D04 - Native crash (SIGSEGV in RenderThread) seen once on an unstable emulator | Seen once on 2026-10-29 13:48 on the Android 17 (API 37) Google Play emulator while its SystemUI was crash-looping. No reliable steps yet. | The app does not crash. | logcat: "Fatal signal 11 (SIGSEGV), code 1 (SEGV_MAPERR), fault addr 0x4 in tid RenderThread (.saleshiker.app)". | 2026-10-29 12:34 | Observation | Medium | P3 - Medium | Needs Decision | Beta backend: accountsbeta.saleshiker.com; see QA comment | docs/DEFECT_TRACKER.md (OBS-002); device crash buffer of the API 37 emulator |  |  |  |  | Not reproduced on the healthy Android 15 emulator in any login run (0 crashes). Not attributed to the app yet: the device itself was failing. Every run saves logcat.crash.txt, so watch for a repeat.

## Campaigns
No# | Module/Screen / Extension | Section / Category | Task / Bugs / Enhacement | Steps to Reproduce (If required) | Expected Result | Actual Result | Date | Issue Type | Severity | Priority | Status | Test Environment | Screenshot/Video | Reopen SS/Video & Description | Assigned To | Closed / Resolved by | Requested by | QA Comment | Developer / Designer Comment | Closed Date
1 | Campaigns (WhatsApp) | Data consistency | MCMP-D01 - Recipient shown as "Replied" while the campaign reports 0 delivered and 0 read | 1. More > Campaigns. 2. Open a campaign with "1 sent" (seen on one Retarget and one Drip campaign, both started 19 Aug). 3. Compare the DELIVERY tiles with RECENT RECIPIENTS. | A recipient who replied has received and read the message, so Delivered and Read are at least 1 (100%). | DELIVERY: Sent 1, Delivered 0 (0%), Read 0 (0%), Failed 0 (0%). RECENT RECIPIENTS lists the only recipient with status "Replied". The same on both campaigns. | 2026-10-30 11:22 | Observation | Low | P3 - Medium | Needs Decision | Beta backend: accountsbeta.saleshiker.com; DQCI7XBU5LXWB6KZ (RMX3997, Android 16); app com.saleshiker.app 1.0.0 | Screenshot: screenshot.png Screenshot: MCMP-019_1.png |  |  |  |  | Seen on 2 campaigns, re-checked twice. Possible cause: delivery/read status callbacks from WhatsApp are not recorded on the beta backend (the sender is a test number), while the reply is. Needs a backend check before it is called an app bug. Automated test MCMP-019 (test/specs/regression/campaign-detail.spec.ts) fails while this persists. Last automated check: 30-Oct-2026 MCMP-019 FAIL (run 20261030-171502-full) - still reproduces.
2 | Campaigns (WhatsApp) | Search | MCMP-D02 - Campaign search ignores type and status although the empty state says to search by them | 1. More > Campaigns. 2. Search "paused" (4 paused campaigns exist), then "active" (2 exist). 3. Search "drip" (5 Drip campaigns exist). | The empty state says "Try another name, type or status.", so "paused" lists the 4 paused campaigns, "active" the 2 active ones and "drip" all 5 Drip campaigns. Alternatively, the hint names only what search supports. | "paused", "Paused" and "active" show "No campaigns found". "drip" lists 1 campaign: the one with "drip" in its name. Search matches names only. | 2026-10-30 11:22 | Bug | Low | P4 - Low | Open | Beta backend: accountsbeta.saleshiker.com; DQCI7XBU5LXWB6KZ (RMX3997, Android 16); app com.saleshiker.app 1.0.0 | Screenshot: screenshot.png Screenshot: MCMP-012_search_Active.png Screenshot: MCMP-012_search_Drip.png |  |  |  |  | Reproduced with 4 search terms. Filters by type/status work through the chips (MCMP-004, MCMP-005). Fix either the search or the hint text. Automated test MCMP-012 (test/specs/regression/campaigns-search.spec.ts) fails while this persists. Last automated check: 30-Oct-2026 MCMP-012 FAIL (run 20261030-173959-single-MCMP-012) - still reproduces.
3 | Campaigns (WhatsApp) | Usability | MCMP-D03 - With the keyboard open, the first tap on "Clear Filters" only closes the keyboard | 1. More > Campaigns. 2. Search for a name that does not exist (keyboard stays open). 3. Tap "Clear Filters" once. | One tap clears the search and filters. | The first tap only hides the keyboard; a second tap is needed. | 2026-10-30 11:22 | Observation | Low | P4 - Low | Needs Decision | Beta backend: accountsbeta.saleshiker.com; see QA comment | Screenshot: MCMP-010_empty_state.png |  |  |  |  | Typical React Native keyboardShouldPersistTaps default. The automated test closes the keyboard first so it checks the button itself. Product to decide.

## Broadcasts
No# | Module/Screen / Extension | Section / Category | Task / Bugs / Enhacement | Steps to Reproduce (If required) | Expected Result | Actual Result | Date | Issue Type | Severity | Priority | Status | Test Environment | Screenshot/Video | Reopen SS/Video & Description | Assigned To | Closed / Resolved by | Requested by | QA Comment | Developer / Designer Comment | Closed Date
1 | Broadcasts (WhatsApp) | Send safety | MBRD-D01 - For a Tags audience, neither the review nor the send confirmation says how many contacts will receive the broadcast | 1. Broadcasts > New Broadcast. 2. Audience: Tags, add a tag. 3. Pick a template and go to Review. 4. Tap Send Broadcast. | Before sending, the user sees how many contacts the tag reaches, as for the other audiences ("All contacts: 3,01,064 contacts", segment "3 contacts match.", review "Audience, 3 contacts"). | Step 1 shows no count for tags. The review shows only "Audience, Tags: <tag>" and the confirmation only "Tags: <tag>. Sending starts now." The count appears only after sending (detail: "Tags: <tag>. 2 contacts"). Contacts search does not find contacts by tag either, so the reach cannot be checked on the phone at all. | 2026-10-31 08:19 | Bug | Medium | P2 - High | Open | Beta backend: accountsbeta.saleshiker.com; DQCI7XBU5LXWB6KZ (RMX3997, Android 16); app com.saleshiker.app 1.0.0 | Screenshot: screenshot.png |  |  |  |  | A common tag can reach thousands of contacts with no warning. Seen on every Tags review (3 times). Automated test MBRD-012 (test/specs/regression/broadcast-wizard.spec.ts) fails while this persists. The send test (MBRD-020) works around it by checking each allowlisted contact's tag first and the recipients afterwards. Last automated check: 31-Oct-2026 MBRD-012 FAIL (run 20261031-133943-full) - still reproduces.
2 | Broadcasts (WhatsApp) | Usability | MBRD-D02 - Template search keeps the previous text, and typing after tapping the field inserts in the middle of it | 1. New Broadcast > step 2 > open the template picker and search "call_phone_message". 2. Pick a template, then open the picker again. 3. Tap the search field and type. | The picker opens with an empty search, or tapping puts the cursor at the end. | The old text is still there and the cursor lands where the field was tapped, producing e.g. "call_phone_mescall_phone_messagesage" and "No templates found". | 2026-10-31 08:19 | Observation | Low | P4 - Low | Needs Decision | Beta backend: accountsbeta.saleshiker.com; see QA comment | Screenshot: screenshot.png |  |  |  |  | Seen once during exploration. The automated tests clear the field with its X before typing.

## Failures to triage
Test ID | Module | Test | Failure | Date | Evidence | Classification | Notes
MBRD-001 | Broadcasts | Broadcast list opens with status filters and New Broadcast starts the wizard | Can't call getText on element with selector "android=new UiSelector().textMatches("[0-9,]+ broadcasts?")" because element wasn't found | 2026-10-31 08:10 | Screenshot | To triage
MBRD-002 | Broadcasts | Step 1 starts with no audience chosen and the first connected number as sender | WebDriverError: java.util.ArrayList$ListItr cannot be cast to org.eclipse.wst.xml.xpath2.processor.internal.types.NodeType. Try changing the 'enforceXPath1' driver setting to 'true' in order to workaround the problem. when running "elements" with method "POST" | 2026-10-31 08:10 | Screenshot | To triage
MBRD-003 | Broadcasts | Step 1 blocks Next without a name or an audience | tag error: expected false to equal true | 2026-10-31 08:10 | Screenshot | To triage
MBRD-005 | Broadcasts | Saved list and Segment pickers offer named audiences with their sizes | waitUntil condition failed with the following reason: WebDriverError: java.util.ArrayList$ListItr cannot be cast to org.eclipse.wst.xml.xpath2.processor.internal.types.NodeType. Try changing the 'enforceXPath1' driver setting to 'true' in order to workaround the problem. when running "elements" with method "POST" | 2026-10-31 08:10 | Screenshot | To triage
MBRD-007 | Broadcasts | Template search is case-insensitive and reports no match | element ("~Search templates") still not displayed after 15000ms | 2026-10-31 08:10 | Screenshot | To triage
MBRD-009 | Broadcasts | Review summarises the choices, defaults to Send now and asks before sending | waitUntil condition failed with the following reason: WebDriverError: java.util.ArrayList$ListItr cannot be cast to org.eclipse.wst.xml.xpath2.processor.internal.types.NodeType. Try changing the 'enforceXPath1' driver setting to 'true' in order to workaround the problem. when running "elements" with method "POST" | 2026-10-31 08:10 | Screenshot | To triage
MBRD-010 | Broadcasts | Back keeps the entries of earlier steps | element ("~Search templates") still not displayed after 15000ms | 2026-10-31 08:10 | Screenshot | To triage
MBRD-011 | Broadcasts | Closing asks to discard, Cancel keeps editing and Discard saves nothing | Test skipped due to failure in hook ""before each" hook: wrappedHook for "MBRD-011 Closing asks to discard, Cancel keeps editing and Discard saves nothing"": HomePage not shown within 1000 ms | 2026-10-31 08:10 | 20261031-133943-full | To triage
MBRD-020 | Broadcasts | Create and send a broadcast to the allowlisted tag, then check its recipients | waitUntil condition failed with the following reason: WebDriverError: java.util.ArrayList$ListItr cannot be cast to org.eclipse.wst.xml.xpath2.processor.internal.types.NodeType. Try changing the 'enforceXPath1' driver setting to 'true' in order to workaround the problem. when running "elements" with method "POST" | 2026-10-31 08:10 | Screenshot | To triage